## DEFECT REPORT
Project Name:JPETSTORE Prepared By:Kailash Satasiya Date:3-03-2024
Defect ID | Test Case ID | Defect Summary | Reproduced Steps | Test Data | Defect Type | Severity | Priority | Expected o/p | Actual o/p | Tester Name | Attechement | Status
1 | 26 | Check the "Return to FI-SW-01" link. | 1.Open the browser like google chrome. 2.Add URL to the address bar of the browser. 3.Press Enter to open. 4.click on the " fish button". 5.Click on the "product id FI-SW-01 button". 6.Click on the "item id EST-1". | NA | Usability | Medium | Medium | It will open the "item detail page". | It will show name instead of product id. | kailash satasiya | https://drive.google.com/file/d/18w7M6-E4eZMlcO_m675qbUzXnbI384ZM/view?usp=sharing | Open
2 | 32 | Check the "Continue" button from the checkout page. Enter invalid card type. | 1.Open the browser like google chrome. 2.Add URL to the address bar of the browser. 3.Press Enter to open. 4.click on the " fish button". 5.Click on the "product id button". 6.Click on the "add to cart button". 7.Click on the "procced to checkout button". 8.Click on the "continue"button. | Card type:american express. Card number:999 9999 9999 9999. Expiry date:12/03. | Usability | High | High | It will open the "conformation page". | It will redirect to conformation page with wrong card tye . | kailash satasiya | https://drive.google.com/file/d/1u-xB46xgNWELfdKhwLjt5an13my1t5aW/view?usp=sharing | Open
3 | 33 | Check the "Continue" button from the checkout page. Enter invalid card number. | 1.Open the browser like google chrome. 2.Add URL to the address bar of the browser. 3.Press Enter to open. 4.Click on the "cart button". 5.click on the " fish button". 6.Click on the "product id button". 7.Click on the "add to cart button". 8.Click on the "procced to checkout button". 9.Click on the "continue"button. | Card type:american express. Card number:123 1234 3456 4567. Expiry date:12/03. | Finctionality | High | High | It will open the "conformation page". | It will redirect to conformation page with wrong card number. | kailash satasiya | https://drive.google.com/file/d/1h_bJFA1w6Yxif5jZ7L0aSXeYL_031DcC/view?usp=sharing | Open
4 | 34 | Check the "Continue" button from the checkout page. Enter invalid expiry date. | 1.Open the browser like google chrome. 2.Add URL to the address bar of the browser. 3.Press Enter to open. 4.click on the " fish button". 5.Click on the "product id button". 6.Click on the "add to cart button". 7.Click on the "procced to checkout button". 8.Click on the "continue"button. | Card type:american express. Card number:123 1234 3456 4567. Expiry date:06/23 | Functionality | High | High | It will open the "conformation page". | It will redirect to conformation page with wrong expiry date. | kailash satasiya | https://drive.google.com/file/d/1vEfYE1BcThROw9ffcQJHG9ZZowOnQf20/view?usp=sharing | Open